## All Items
2
Proposed Items with Resource Considerations in Priority Order
Priority # | # from March 8 | Project/Task* | Project Objective | Project Size | Start Date | Finish Date | Estimated Budget (not including staff time) | Allocated Budget | Budget Expended/ Encumbered | Commission | Department | Goal Category | General Plan Guiding Principle | Staff Recommendation (Include, Not Include, Not Include-Operational) | Justification / Considerations | Councilmember Rating | Councilmember Rating | Councilmember Rating | Councilmember Rating | Councilmember Rating | Average Rating | Sum Rating
1 | 65 | Consider options to develop ELI and BMR housing units for Developmentally Disabled individuals on City-owned property along Mary Avenue as well as the Outback Steakhouse location Current City Work Program Item Proposed to continue by Housing Commission | Identify ways to build ELI and BMR housing units for developmentally disabled. Investigate additional sites for BMR or ELI housing. | Large | 2019-07-01 | 2023-12-30 | 250000 | 250000 | 12540 | Planning Commission Housing Commission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity | Include | Continue interdepartmental coordination and processing. |  | 5 | 5 | 3 | 3 | 4 | 16
2 | 57 | Memorial Park Improvements Current City Work Program Item Proposed to continue by Parks and Recreation Commission (Also Part of CIP) | Implement projects for Memorial Park improvements including: 1. Memorial Park - Pond Repurposing 2. Memorial Park - Amphitheater Improvements 3. Memorial Park - Specific Plan Design | Large | 2021-07-01 | 2024-06-30 | 4650000 | 4650000 | 130000 | Parks & Recreation Commission | Public Works/ Parks and Recreation | Quality of Life | 1. Develop Cohesive Neighborhoods 7. Ensure Attractive Community Design | Include | Work is in progress but will not be completed by end of FY 21-22. |  | 5 | 5 | 3 | 3 | 4 | 16
3 | 17 and 54 | 1) Dogs Off Leash Area (DOLA) Current City Work Program Item Proposed to continue by Parks and Recreation Commission | Revised Objective: Standardize the process to create DOLA trial programs, with no more than two trials running at a time. Respond and evaluate community-driven DOLA proposals to implement additional DOLAs throughout the City. ______________________________________________________ The Revised Objective was developed by combining the below objectives: FY 21-22 City Work Program: Identify additional areas suitable for permitting dogs to be off leash and establish one such area, if the current trial period is successful. Parks and Recreation Commission: Standardize the process to create DOLA trial programs, with no more than two trials running at a time. Respond and evaluate community-driven DOLA proposals to implement additional DOLAs throughout the City. | Large | 2022-10-01 | 2023-06-30 | 5000 | 5000 | 0 | Parks and Recreation Commission | Parks and Recreation | Quality of Life | 5. Ensure a Balanced Community | Include | Trial ended October 2021. The ongoing program is to be observed for one year before another such area can be established. |  | 3 | 3 | 5 | 3 | 3.5 | 14
4 | 2 and 61 | 2) Vision Zero Current City Work Program Item Proposed to continue by Bike Ped Commission | Revised Objective: Develop a Vision Zero Policy and Action Plan and hire a consultant. The Plan will guide policies and programs with the goal of eliminating fatalities on Cupertino roadways. Special emphasis will be placed on routes to, and streets surrounding, Cupertino schools. ______________________________________________________ The Revised Objective was developed by combining the below objectives: FY 21-22 City Work Program: Develop a Vision Zero Policy and Action Plan. The Plan will guide policies and programs with the goal of eliminating fatalities on Cupertino roadways. Special emphasis will be placed on routes to, and streets surrounding, Cupertino schools. Bike Ped Commission: Retain consultant to complete the development of the Vision Zero program, including finalization of policies and action plans. | Medium | 2022-07-01 08:00 | 2023-06-30 17:00 | 80,000 Evaluation of the City's needs over the course of the year have revealed that a budget allocation will be necessary to hire a consultant to assist with completing the rollout of the Vision Zero program. | 0 | 0 | Bicycle Pedestrian Commission | Public Works | Transportation | 3. Improve Connectivity 4. Enhance Mobility | Include | Vision Zero is a current FY 21-22 City Work Program item proposed to continue. Evaluation of the City's needs over the course of the year have revealed that a budget allocation will be necessary to hire a consultant to assist with completing the rollout of the Vision Zero program. |  | 5 | 3 | 3 | 3 | 3.5 | 14
5 | 59 | Lawrence Mitty - Master Plan Current City Work Program Item (Also Part of CIP) | Development project for Lawrence Mitty will be included in the CIP. Programming, Outreach, & Design with outreach expected to start by Q3 FY 21-22. | Medium | 2019-07-01 | 2023-08-31 | 5430000 | 5430000 | 313140 | Parks and Recreation Commission | Public Works/ Parks and Recreation | Quality of Life | 1. Develop Cohesive Neighborhoods 7. Ensure Attractive Community Design | Include | Work is in progress but will not be completed by end of FY 21-22. |  | 5 | 5 | 3 | 0 | 3.25 | 13
6 | 8 and 49 | Cupertino Store Implementation Councilmember Proposal Staff Proposal Fine Arts Commission Proposal | Revised Objective: Implement the Cupertino Store plan, which will be adopted by Council as part of the current City Work Program Item "Cupertino Store at Chamber of Commerce". This would include identifying a location if one is not identified in fiscal year 2021-2022. With some help from the Fine Arts Commission for some of the items with art designed by community members, items would be designed and selected for the store, for sale to the public, and also available for exchange purposes for formal delegations to and from the City, with an at-cost charge structure for the latter purposes. ______________________________________________________ The Revised Objective was developed by combining the below objectives: Staff Proposal: Implement the Cupertino Store plan, which will be adopted by Council by the end of FY 2021-22 as part of the current City Work Program Item "Cupertino Store at Chamber of Commerce". Fine Arts Commission: Art designed by community members and approved by Fine Arts Commission for Art store to provide giveaways to visiting Mayors, sister cities, commissioners from other cities, etc. Councilmember Proposal: Direction to staff previously was to investigate multiple site possibilities in this current (2021-2022) fiscal year. As such, several additional possible sites come to mind, but are not limited to: - Quinlan Center - Library - City Hall There are likely to be more feasible places. This combined item would first identify a location if one is not identified in fiscal 2021-2022. In the upcoming 2022-2023 fiscal year, with some help from the Fine Arts Commission for some of the items, items would be designed and selected for the store, for sale to the public and also available for exchange purposes for formal delegations to and from the City, with an at-cost charge structure for the latter purposes. Notes: Combines two items and fulfills need of having Cupertino-branded material available to the public. | Medium (Assumes either Chamber provides staffing for store or the store is operated at a City-owned location with existing merchandise sales.) Large (If not at locations as described above, there would be an ongoing need of at least 2-4 staff to operate.) | 2022-07-01 | 2023-06-30 | Budget necessary will depend on the direction of Council once the options are brought for consideration later this year. This could involve annual costs of $80,000-$100,000 for management and operations to be handled by the Chamber. An estimated $30,000 would be needed for merchandise. If store is not staffed by the Chamber or operated at a City-owned location with existing merchandise sales, additonal staff costs are estimated at $285,000 annually. | 5000 | 0 | Fine Arts Commission | City Manager's Office | Public Engagement and Transparency | 6. Support Vibrant and Mixed-Use Businesses | Include | Once the draft proposal for the Cupertino store is adopted by Council, the next step will be the implementation phase, which will take place in FY 22-23. It is recommended that Council include this in the FY 22-23 City Work Program so that staff is able to work on the Council-approved concept and begin the implementation of the Cupertino Store. |  | 1 | 3 | 3 | 5 | 3 | 12
7 | 67 | Development Accountability Current City Work Program Item Proposed to continue by Planning Commission | Analyze methods to limit the implementation timeline for entitled/future projects and encourage development. Monitor implementation of development agreements and conditions of approval. Review and establish accountability in the project approval process. | Medium | 2020-03-01 08:00 | 2023-06-30 17:00 | 10000 | 10000 | 0 | Planning Commission | Community Development | Quality of Life | 5. Ensure a Balanced Community 6. Support Vibrant and Mixed-Use Businesses | Include | Staffing challenges. |  | 5 | 3 | 3 | 0 | 2.75 | 11
8 | 10 | 2) Homeless Jobs Program Current City Work Program Item Proposed to continue by Housing Commission | Create a jobs program for up to 2 individuals for 6 months. | Medium | 2021-07-01 | 2023-06-30 | 190,000 (An additional $190,000 would be needed to continue the program beyond this fiscal year.) | 200000 | 169060 | Housing Comission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity | Not Include | Current FY 21-22 City Work Program item. Program will conclude in June 2022. Additional resources and further coordination with provider necessary to extend. |  | 3 | 5 | 3 | 0 | 2.75 | 11
9 | 63 | RHNA related General Plan updates and rezoning (Housing Element) Current City Work Program Item Proposed to continue by Planning Commission | Review preliminary RHNA numbers. Look at strategies for RHNA compliance including evaluating sites for potential upzoning, and jobs-housing ratio and statistics. Identify Priority Housing sites, update Housing Element and complete rezoning by September 2023. | Large | 2020-05-19 08:00 | 2023-01-31 | 1070000 | 1070000 | 748040 | Planning Commission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity | Include | This is an ongoing project. |  | 5 | 3 | 3 | 0 | 2.75 | 11
10 | 69 | Residential and Mixed-Use Residential Design Standards Current City Work Program Item Proposed to continue by Planning Commission | Create objective design standards for residential and mixed-use residential projects, including ensuring adequate buffers from neighboring low-density residential development. | Medium | 2020-10-09 08:00 | 2023-06-30 | 240000 | 240000 | 196200 | Planning Commission | Community Development | Quality of Life | 1. Develop Cohesive Neighborhoods 6. Support Vibrant and Mixed-Use Businesses 7. Ensure Attractive Community Design | Include | Staffing challenges. Ongoing project important for the Housing Element implementation. |  | 5 | 3 | 3 | 0 | 2.75 | 11
11 | 64 | Sign Ordinance Update Current City Work Program Item Proposed to continue by Planning Commission | Update existing provisions, particularly in the temporary sign regulations. | Small | 2020-05-13 08:00 | 2022-12-30 | 25000 | 25000 | 0 | Planning Commission | Community Development | Quality of Life |  | Include | On pause due to City Attorney changeover. |  | 5 | 3 | 3 | 0 | 2.75 | 11
12 | 48 | Economic Development Strategy Staff Proposal | The updated Economic Development Strategy will aim to understand the current business environment and market trends. This framework will formulate short- and long-term economic development policies and develop goals and objectives to encourage economic recovery and growth. | Large | 2022-07-01 | 2023-06-30 | 120000 | 30000 | 30000 | Economic Development Committee | City Manager's Office | Sustainability and Fiscal Strategic | 6. Support Vibrant and Mixed-Use Businesses | Include | Cupertino’s Economic Development (ED) Strategy was last updated in 2016. Business models, operations, as well as trends have significantly shifted due to the pandemic. Council has expressed an interest in updating the ED Strategy, which is especially important now as we emerge from the pandemic and move towards recovery. It is recommeded that Council include this in the FY 22-23 City Work Program so that there are timely goals and objectives clearly outlined to further economic vitatility in Cupertino. |  | 3 | 0 | 1 | 5 | 2.25 | 9
13 | 37 and 47 | Electrification Study Staff Proposal Sustainability Commission Proposal | Revised Objective: Conduct public outreach, policy research, and coordinate with regional efforts to develop policy options for electrification of Cupertino's buildings and transportation systems. ______________________________________________________ The Revised Objective was developed by combining the below objectives: Sustainability Commission: Conduct public outreach, conduct policy research, and coordinate with the regional efforts on electrification of buildings and transportation systems. Staff Proposal: Examine options to encourage rapid electrification of buildings, i.e. via the update of the building electrification reach codes. | Medium | 2022-10-01 | 2023-06-30 | 50000 | 0 | 0 | Sustainability Commission | City Manager's Office | Sustainability and Fiscal Strategic | 10. Preserve the Environment | Include | The Draft Climate Action Plan identifies several high-impact measures. Developing policy options and conducting public outreach specifically for residential and non-residential existing buildings electrification is a key step in achieving the 2030 and 2040 greenhouse gas reduction targets. |  | 3 | 3 | 1 | 1 | 2 | 8
14 | 55 | Lehigh and Stevens Creek Quarry Current City Work Program Item | Monitor and report on Lehigh and Stevens Creek Quarries. Utilize IOT sensors to measure noise, particulate, and pollution levels at Lehigh and Stevens Creek Quarry. | Medium | 2020-09-07 | 2022-06-30 | 478,050 (Includes $62,500 for noise and pollution monitoring and $415,550 for legal fees) | 478,050 (Includes $62,500 for noise and pollution monitoring and $415,550 for legal fees) | 279,090 (Includes $17,500 spent for noise and pollution monitoring and $261,590 for legal fees) | TICC | Public Works/ Innovation Technology | Quality of Life | 10. Preserve the Environment | Include | Delayed Implementation due to prolonged contract negotiations and supply chain issues. This is an ongoing effort. |  | 1 | 3 | 1 | 3 | 2 | 8
15 | 52 | Senior Strategy Current City Work Program Item | Address the needs of seniors in collaboration with the City Council and Commissions. Needs to address include technology resources, housing, food supply, transportation, and mental and physical health and wellbeing. | Medium | 2021-11-01 | 2023-01-10 | 34000 | 34000 | 1330 | Parks and Recreation Commission | Parks and Recreation | Public Engagement and Transparency | 8. Embrace Diversity | Include | Extensive community engagement, staffing vacancies, COVID. |  | 0 | 3 | 5 | 0 | 2 | 8
16 | 29 and 41 | 1) License Plate Readers Public Safety Commission Proposal Technology Information and Communications Commission Proposal | Revised Objective: 1. Research Automated License Plate Reader (ALPR) systems 2. Research state laws, privacy concerns, and regulations related to ALPR 3. Compare fixed location, mobile (in-car), and portable (trailer ALPRs) 4. Identify outreach and engagement strategies used by other jurisdictions using ALPR 5. Assess locations for fixed ALPR in Cupertino 6. Estimate ALPR costs for installation, monitoring, and maintenance (Consider: Cameras, LPR, Safe-Exchange Zone, Pilot cameras in a residential areas, and commercial developments Research best practices from other similar jurisdictions) 7. In partnership with the County Sheriff, install ALPR devices for the automated detection of license plates. This data will only be for official law enforcement purposes, including identifying stolen or wanted vehicles, stolen license plates and missing persons. It may also be used to gather information related to active warrants, homeland security, electronic surveillance, suspect interdiction, and stolen property recovery. ______________________________________________________ The Revised Objective was developed by combining the below objectives: Public Safety Commission: 1. Research Automated License Plate Reader (ALPR) systems 2. Research state laws, privacy concerns, and regulations related to ALPR 3. Compare fixed location, mobile (in-car), and portable (trailer ALPRs) 4. Identify outreach and engagement strategies used by other jurisdictions using ALPR 5. Assess locations for fixed ALPR in Cupertino 6. Estimate ALPR costs for installation, monitoring, and maintenance (Consider: Cameras, LPR, Safe-Exchange Zone, Pilot cameras in a residential areas, and commercial developments Research best practices from other similar jurisdictions) Technology Information and Communications Commission: In partnership with the County Sheriff, install LPR devices for the automated detection of license plates. This data will only be for official law enforcement purposes, including identifying stolen or wanted vehicles, stolen license plates and missing persons. It may also be used to gather information related to active warrants, homeland security, electronic surveillance, suspect interdiction, and stolen property recovery. | Extra-Large | 2022-07-01 | 2023-06-01 | 60,000 initial and 50,000 annually Estimated 20 cameras at $2,500 based on City of Saratoga and City of Los Altos Hills contracts with approximately $10,000 installation costs | 0 | 0 | Public Safety Commission/ TICC | City Manager's Office/ Innovation Technology | Quality of Life | 2. Improve Public Health and Safety | Include | Cities of Los Gatos, Saratoga, and Los Altos Hills have similar projects and addressed some privacy concerns with Santa Clara County Sheriff's Office. |  | 3 | 1 | 3 | 0 | 1.75 | 7
17 | 23 | 2) 5G Ordinance Planning Commission Proposal | Adopt regulations based on aesthetics. | Medium | 2022-07-01 | 2023-06-30 17:00 | 0 | 0 | 0 |  | Public Works | Quality of Life | 7. Ensure Attractive Community Design | Not Include | The City's Public Works Department is already drafting 5G regulations which will be completed this fiscal year. |  | 0 | 3 | 0 | 3 | 1.5 | 6
18 | 66 | City Plan to End Homelessness Current City Work Program Item Also proposed to continue by Housing Commission | Draft an Implementation Plan to the Santa Clara County Community Plan to End Homelessness 2020-25 to create a roadmap for addressing homelessness in Cupertino. | Large | 2019-07-01 08:00 | 2022-09-30 | 300,000 (no additional budget needed beyond what is already allocated) | 300000 | 0 | Housing Commission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity | Include | To accommodate additional community outreach. |  | 3 | 3 | 0 | 0 | 1.5 | 6
19 | 68 | Review and Update General Plan (GP) and Municipal Code Current City Work Program Item Also proposed to continue by Planning Commission | 1. Amend General Plan & Municipal Code & zoning code to provide objective standards as identified in 2019/2020 evaluation. 2. Re-evaluate the Heart of the City Specific Plan for sections of the plan that could be clarified and updated easily with objective standards. | Large | 2019-06-03 08:00 | 2023-06-01 | 500000 | 500000 | 224200 | Planning Commission | Community Development | Quality of Life | 1. Develop Cohesive Neighborhoods 3. Ensure a Balanced Community 7. Ensure Attractive Community Design | Include | Phase 3 of project completed. Other updates to be considered as the need arises. |  | 0 | 0 | 5 | 1 | 1.5 | 6
43 | 60 | Seismic Retrofits and Upgrades to Existing City Hall (formerly "Investigate Alternatives to City Hall") Current City Work Program Item (Also Part of CIP) | Examine seismic retrofits, upgrades, and remodels to existing City Hall. Remove allocations from budget to a new City Hall. | Large | 2020-05-01 08:00 | 2023-06-30 | 500000 | 500000 | 500000 |  | Public Works | Sustainability and Fiscal Strategy | 2. Improve Public Health and Safety | Include | This is an ongoing effort. |  | 1 | 1 | 1 | 3 (needs public involvement) | 1 1.5 | 3 6
20 | 56 | 10455 Torre Avenue Improvements Programming & Feasibility Current City Work Program Item (Also Part of CIP) | Program, plan, and build facility improvements, including seismic, utility and ADA upgrades, for the long-term use of this facility. The scope of work will include public outreach, programming, planning, design, and construction. | Large | 2021-07-01 | 2023-06-30 | 3000000 | 3000000 | 77560 |  | Public Works | Sustainability and Fiscal Strategy | 2. Improve Public Health and Safety | Include | Work is in progress but will not be completed by end of FY 21-22. |  | 1 | 3 | 0 | 1 | 1.25 | 5
21 | 51 | Analyze Potential Revenue Measures Staff Proposal | Analyze potential revenue measures, such as transient occupancy tax, sales tax, property tax, and utility users tax, to address possible future financing challenges | Medium | 2022-07-01 | 2022-11-01 | 50000 | 0 | 0 |  | Administrative Services | Sustainability and Fiscal Strategy | 11. Ensure Fiscal Self Reliance | Include | The City has a significant list of unfunded Capital Improvement Program (CIP) projects that, if approved, will require substantial financing. |  | 3 | 1 | 1 | 0 | 1.25 | 5
22 | 15 | 2) Artwork at the Library/Exhibits/Poetry and Art Day Library Commission Proposal | Collaborate with groups such as the Fine Arts Commission and Cupertino Poet Laureate to display artwork, including exhibits, at the Library. Exhibits could potentially be around the library and in the new programming space. Examples could be potential galleries, a poetry/art show, cultural documents and artifacts, or other fascinating exhibits. | Small | 2022-07-01 | 2023-06-01 | 10000 | 0 | 0 | Library Commission | Parks and Recreation | Quality of Life | 9. Support Education | Not Include - Operational through the Library | Currently there are already artwork displays in the library, one being from the Fine Arts Commission. Displays and potential exhibits would be operational through the library. |  | 0 | 0 | 5 | 0 | 1.25 | 5
23 | 1 | 1) Bicycle Facilities Bike Ped Commission Proposal | Increase the inventory of bicycle facilities and amenities, such as bike racks, citywide. | Medium | 2022-09-01 | 2023-06-30 | 50000 | 0 | 0 | Bicycle Pedestrian Commission | Public Works | Transportation | 4. Enhance Mobility | Include | Item falls within the purview of the Bicycle Pedestrain Commission and can be managed with existing staff resources. Achieving the objective will encourage bicycling within Cupertino, consistent with City's overall goals. |  | 3 | 0 | 1 | 1 | 1.25 | 5
24 | 12 | 4) Housing Programs for De Anza College Students Previous City Work Program Item Housing Commission Proposal | Explore solutions for homeless and housing insecure students. Assist, as appropriate in, the long-term development of De-Anza student housing. Investigate partnership with De Anza on student housing and transportation solutions. | Small | 2020-07-01 | 2023-06-30 | 25000 | 25000 | 25000 | Housing Commission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity 9. Support Education | Include | Previous FY 20-21 City Work Program item. Program/contract will conclude in June 2022 and De Anza College has also expressed interest in extending the program. |  | 3 | 0 | 1 | 1 | 1.25 | 5
25 | Councilmember Proposed Item | Integrated Plan for Community Engagement Councilmember Proposal | Create Integrated Plan and Database for Community Engagement so that we do no start from scratch with each project. The plan should include all possible outreach channels, traditional media, newspaper, including Chinese and other languages, city channel, the Scene, social media and influencers. community leaders, community groups, HOAs, block leader programs, Chamber and other business groups etc. Explore the possibility for Library and Community Engagement Commission so that the Library Commission could help review and update this plan as needed. Notes: - The City continues to waste precious time since each project appears to be using an ad hoc approach for outreach. Each new project can utulize database and plan to customize for the project needd. - Assign to Library Commission to explore possibiliiites. The Commission could put Library items first so that the Librarians only need to attend the first half of the meeting. | Extra-Large | 2022-07-02 | 2023-06-30 | 30,000 Additional budget may be required to implement the plan once it is completed as it may require additional printing, mailing, translation, etc. | 0 | 0 |  | City Manager's Office | Public Engagement and Transparency | 12. Ensure a Responsive Govenment | For the Plan itself: Not Include - Operational For Exploring Library and Community Engagement Commission: Not Include | The Plan is already being worked on as part of operations and was launched with the Study Session on December 7, 2021. |  |  |  | 5 |  |  | 5
26 | Councilmember Proposed Item | Lawrence Mitty - Master Plan (combining 21 and 59 from [original attachment C] list with supplemental direction) Councilmember Proposal | Incorporates Items 21 and 59 in [original attachment C] list, with the following additions: - Hire a dedicated Project Manager by the end of Q1 FY2022-2023 for the development of the Lawrence-Mitty Park. - Review and modify the current timetable, and bring back an updated schedule to City Council by November 2022 with an aim of delivering a completed park to the public in as timely and effective a manner as possible. Notes: A dedicated project manager should will help to ensure timely completion of the project. A project manager will also help ensure that this traditionally park-under-served area receives appropriate outreach and becomes engaged both in the process of developing a park, and in ongoing community activities which are an integral part of maintaining the space. | Large | 2019-07-01 | 2023-08-31 | 5,430,000 A standalone PM would cost the City an estimated $425,000 annually, and would not shorten the timeline of the project. | 5430000 | 313140 | Parks and Recreation Commission | Public Works/ Parks and Recreation | Quality of Life | 1. Develop Cohesive Neighborhoods 7. Ensure Attractive Community Design | Not Include | The project is underway with an exceptionally talented outside consultant and management team. Public Works and Parks and Recreation Departments are actively involved with this consultant team to move the project forward. It is a project with the highest level of priority. The site analysis and reporting work is underway, in addition to the Community Outreach work. The Community Outreach is vital to the foundation of the project's success. Initial designs will be developed after Council, Commission, and the Community have provided feedback via a survey, meetings, etc. The input will continue through July. At that point, Design options will be developed, and more feedback will be sought from Council, Commissions and the Community. The Design Phase is anticipated to continue until the end of February 2023. The Environmental report will be developed concurrently and submitted for review at the same time. We are confident that the current timeline is the most effective and efficient project schedule to allow for real community engagement while also producing productive and innovative design solutions. Adding additional Council review sessions will delay the process. A standalone PM would cost the City an estimated $425,000 annually, and would not shorten the timeline of the project. |  |  |  |  | 5 |  | 5
27 | Councilmember Proposed Item | Resident Engagement Councilmember Proposal | Increase resident engagement in Cupertino. For example: - Greater participation in surveys (possibly incentivizing surveys with gift cards) - Greater interaction with the community (e.g. tabling with swag, encouraging sign-ups for updates) -Greater use of partner outlets (e.g. at Library, Chamber, DeAnza, CUSD, FUHSD) | Large | 2022-07-01 | 2023-06-30 | 30000 | 0 | 0 |  | City Manager's Office | Public Engagement and Transparency | 12. Ensure a Responsive Govenment | Include | In order to do this effectively, additional staff will be required. |  |  | 5 |  |  |  | 5
28 | 33 and 50 | Safe Gun Storage Ordinance Staff Proposal Public Safety Commission Proposal | Revised Objective: Research best practices for safe gun storage from neighboring jurisdictions. Adopt safe gun storage ordinance to increase public safety for residents. ______________________________________________________ The Revised Objective was developed by combining the below objectives: Public Safety Commission: Research best practices from neighboring jurisdictions. Staff Proposal: Adopt safe gun storage ordinance to increase public safety for residents. | Large | 2022-07-01 | 2023-06-30 | 12000 | 0 | 0 | Public Safety Commission | City Manager's Office | Quality of Life | 2. Improve Public Health and Safety | Include | Council expressed an interest in this item earlier this fiscal year. Recommended only if the Council has a strong willingness to approach a very difficult process with strong opinions from outside the City. |  | 3 | 1 | 0 | 1 | 1.25 | 5
29 | 58 | Shuttle Bus Pilot Program Implementation Current City Work Program Item | Community shuttle bus 18-month pilot program to increase connectivity throughout the City, nearby medical locations, and Caltrain in Sunnyvale. Explore complimentary opportunities to expand into other cities. | Large | 2019-10-29 08:00 | 2022-06-30 | 1750000 | 1750000 | 1750000 |  | Public Works | Transportation | 4. Enhance Mobility | Include | Work is in progress but will not be completed by end of FY 21-22. |  | 3 | 1 | 0 | 1 | 1.25 | 5
30 | Councilmember Proposed Item | Student Internship Program Councilmember Proposal | Implement a trial student summer internship program with the City of Cupertino. Initial year will be on a limited basis. If approved, applications will be sought for one-, two- or three-week internships during the summer, with applications to be released in mid-July. Internships will be project-focused, with participating City departments asked to identify a specific project or projects that a student intern can undertake. The internships will have a common start date, and include an orientation, group activities and exit interviews. Alternatively, if the time and resources do not permit the City to run a trial program in the upcoming summer of the fiscal year (i.e., Summer 2022), Council may form a subcommittee to share practices for student internships, and to bring a report back to Council at the end of Summer 2022 with recommendations as part of the initiation of a student internship program in Summer 2023. Notes: - Based upon consistent inquiries for such opportunities each year. Furthermore, both the students and City benefit from a program that matches projects that may not otherwise be completed as timely with students looking to learn more about our models of civic engagement and governance. Timing could be challenging for implementing a formal program in Summer 2022. As such, the alternative is recommended to allow for more time to develop such a program. Note that some work program items may provide an ideal fit for generating projects for a student internship program. In the longer-term, once such a program is implemented, it will provide an array opportunities for students to learn about civic engagement while contributing meaningfully to the community. | Medium | 2022-07-01 | 2022-09-30 | 15000 | 0 | 0 | Teen Commission | Administrative Services | Public Engagement and Transparency | 9. Support Education | Include | Assumes the internships would be paid and targeted for high school students. Paid or unpaid internship? |  |  |  |  | 5 |  | 5
31 | Councilmember Proposed Item | Support for the Unhoused combining: - Homeless Jobs Program - City Plan to End Homelessness Councilmember Proposal | These items should be combined into formulating a City plan to address the issue of the unhoused and how to provide services in as effective a manner as possible with the resources available. A specific plan would be generated which includes consideration and recommendations for: - City-driven jobs program. Could be fully independent or work in collaboration with a partner or partners, including the County. - Facility development with supportive services. With non-profit organization partnership, space would be identified and a plan for supportive space with an ultimate aim to provide a pathway to permanent sustained housing would be made. - Funding strategy. This would require significant resources, but the social costs of not addressing this growing issue are more significant. With grant money and possible private partnerships available, the deliverable here would be to provide the City with actionable recommendations for securing financial support for this program. | Unknown at this time | TBD | TBD | Unknown at this time | 0 | 0 | Housing Commission | Community Development | Housing | 5. Ensure a Balanced Community 8. Embrace Diversity | [6 empty] | 5 |  | 5
32 | 40 | Youth and Teen Social Media Engagement Teen Commission Proposal | Increase social media engagement among youth and teens to promote Teen Commission awareness and encourage increased youth participation. | Medium | 2022-07-01 | 2023-06-30 | 1200 | 0 | 0 | Teen Commission | Parks and Recreation/ City Manager's Office | Public Engagement and Transparency | 8. Embrace Diversity | Include | Project would have to be in collaboration with Communications team, which is currently understaffed. |  | 0 | 1 | 1 | 3 | 1.25 | 5
33 | 16 | 3) Community Engagement on Alternative Transportation and Parking Library Commission Proposal | Educate and encourage resident use of alternative transportation to the Library. Install signage to point to overflow parking at Eaton Elementary school. Examine how various changes and developments impact library patrons and residents near and around the Library through the program room expansion, Regnart Creek Trail, bike locks, book drop, as well as continuing the conversation with CUSD regarding Eaton Elementary Parking slots. | Medium | 2022-07-01 | 2023-06-30 | 1500 | 0 | 0 | Library Commission | Parks and Recreation | Public Engagement and Transparency/ Transportation | 4. Enhance Mobility | Include | May be a lengthy process, but parking and transportation education will continue to be needed for library access. |  | 0 | 0 | 1 | 3 | 1 | 4
34 | 19 | 3) Labyrinth Program or Similar Parks and Recreation Commission Proposal | Establish maintenance for the two current labyrinths at McClellan Ranch Preserve and Creekside Park and find ways to enhance recreation at more parks throughout the City with labyrinths or nature play. Engage the community to maintain or create new labyrinths or similar. | Large | 2022-07-01 | 2023-06-30 | 34000 | 0 | 0 | Parks and Recreation Commission | Parks and Recreation | Quality of Life | 5. Ensure a Balanced Community | Not Include - Operational | Could be incorporated into current ongoing CIP projects. (Playground Replacement, Park Amenity Improvements, Memorial Park Improvements, or Lawrence Mitty - Master Plan) |  | 3 | 0 | 1 | 0 | 1 | 4
35 | 62 | Municipal Water System Current City Work Program Item | To analyze and recommend options for the continued operation of the system currently and at the end of lease with San Jose Water Company in November 2024. | Medium | 2020-11-02 08:00 | 2024-10-01 17:00 | 150000 | 150000 | 142750 |  | Public Works | Sustainability and Fiscal Strategy | 11. Ensure Fiscal Seld Reliance | Include | Work is in progress but will not be completed by end of FY 21-22. |  | 0 | 1 | 0 | 3 | 1 | 4
36 | 53 | Blackberry Farm Golf Course Needs Assessment Current City Work Program Item (Also Part of CIP) | Determine short-term and long-term improvements to the golf course and amenities. | Medium | 2020-08-31 08:00 | 2022-08-01 17:00 | 100,000 *Additional funding required for public outreach measures. | 76400 | 47350 | Parks & Recreation Commission | Public Works/ Parks and Recreation | Quality of Life | 5. Ensure a Balanced Community | Include | Extensive community engagement, staffing vacancies, COVID. |  | 1 | 1 | 1 | 0 | 0.75 | 3
37 | 31 | 3) Catalytic Converter Theft Prevention (Nellore) Public Safety Commission Proposal | 1. Warning signs on streets especially the hotspots . A short and crisp message along with the Neighborhood Watch signs on the streets . We at the PSC could help craft this message with the help of the Captain 2. Monthly newsletters providing tips and suggestions for preventive measures the residents can take to help cut the incidents 3. Promote awareness also through neighborhood watch meetings and block party meetings. 4. Many residents are not technical and don't understand what a catalytic convertor looks like or what it does. Help educate them by displaying these online or during various events in booths. 5. Put in section about catalytic convertor theft prevention on our website and educate the residents | Large | 2022-07-01 | 2023-06-01 | 10000 | 0 | 0 | Public Safety Commission | City Manager's Office | Quality of Life | 2. Improve Public Health and Safety | Not include - Operational | The Sheriff's Office incorporates much of the recommended action into regular operations. The Block Leader program will continue to facilitate a relationship with the Sheriff's Office and promote safety and best practices in the community. |  | 0 | 0 | 0 | 3 | 0.75 | 3
38 | Councilmember Proposed Item | Hybrid Meeting for City Council and Commission Meetings Councilmember Proposal | Develop policy and infrastrcture to allow hybrid meetings for both City Council, Commission meetings and future community workshops. This allows seniors, caretakers, parents with young children to participate and speak. Note: Virtual meetings have become the norm nowadays. The community will desire the option to attend a meeting virtually. | Small | 2022-07-05 | 2022-09-30 | 15000 | 0 | 0 |  | Innovation Technology | Public Engagement and Transparency | 12. Ensure a Responsive Govenment |  | The implementation of such a policy will require additional staffing and staff time. |  | 0 | 0 | 3 | 0 | 0.75 | 3
39 | 22 | 1) Impacts to schools Planning Commission Proposal | CUSD is shutting schools down and is running classes in portables. City should ensure our planning policies make schools viable. Assessment or score as in net positive or net negative impact to services (schools, particularly) of a project. | Medium | 2022-07-01 | 2023-06-30 | 30000 | 0 | 0 | Planning Commission | Community Development | Housing | 9. Supporting Education | Not Include | This may be considered by decision makers when determining Housing Element sites. State law prevents the City from considering the fiscal impacts of housing development upon schools, since SB50 states that payment of school impact fees constitutes full and complete mitigation for any school impacts. |  | 0 | 0 | 0 | 3 | 0.75 | 3
40 | Councilmember Proposed Item | Intergenerational Engagement Councilmember Proposal | Many seniors have a wealth of lifelong experiences. Many teens do not have grandparents nearby. Activities cross generations could benefit both. Schools could engage seniors in the community to attend school open house or serve as volunteers, such as reading partners. Notes: -Teen Commission could take the lead on this project | Large | 2022-07-01 | 2023-06-30 | 20000 | 0 | 0 | Teen Commission | Parks and Recreation | Public Engagement and Transparency | 8. Embrace Diversity | Include | Cross generational programs and events are ongoing in the Recreation Department. At the Senior Center, programs such as teens helping seniors with technology, youth and teen performances at the Senior Center, and intergenerational board game playing have been popular. Parks and Recreation could explore collaboration with Teen Commission, Youth Activity Board, and Senior Advisory Council to create a joint program or event. |  |  |  | 3 |  |  | 3
41 | 45 | Lawson Middle School Bikeway Staff Proposal | Retain consultant to prepare feasibility study which will evaluate alternatives that provide a separated bike path for students riding to Lawson Middle School. Feasibility cost will be $40,000. | Medium | 2022-07-01 | 2023-01-31 | 40000 | 0 | 0 | Bicycle Pedestrian Commission | Public Works | Transportation | 3. Improve Connectivity 4. Enhance Mobility | Include | The safety of students riding their bicycles to school, and the encouragement of students to ride who may not currently ride, is a high priority for the City and Transportation Division staff. Completion of a protected bikeway for students riding to Lawson Middle School was identified as a necessary improvement through the City’s Walk Audit process. Successful completion of this improvement is dependent upon third-party consultant analysis and review of alternatives that would be accomplished through the feasibility study process requested with the current proposal. |  | 3 | 0 | 0 | 0 | 0.75 | 3
42 | Councilmember Proposed Item | Mental Health Support Current City Work Program Item Councilmember Proposal | Phase 2 of existing work program item | Unknown at this time | TBD | TBD | Unknown at this time | 10000 | 0 |  | Parks and Recreation | Quality of Life | 8. Embrace Diversity | Include | The current work program item has established a mental health website with resources and information available to the community. Currently working to establish ongoing and greater synergy with county resources, mental health programming, and potential social media campaigns during national suicide prevention month and mental health awareness month. |  |  | 3 |  |  |  | 3
44 | Councilmember Proposed Item | Senior Outreach Project Councilmember Proposal | Create and maintain a periodical newsletter to the senior community (limited paper copies with opt-in email list) containing news from, and opportunities for engagement with, the City of Cupertino. Notes: Based upon a growing and sustained need for neutral and jurisdiction-driven outreach to the senior community. | Large | 2022-07-01 | 2023-06-30 | 156000 | 0 | 0 |  | Parks and Recreation | Public Engagement and Transparency | 8. Embrace Diversity | Include | The Senior Center produces a bi-monthly newsletter that is printed and available at the QCC, Library, Sports Center, Senior Center, City Hall, the Golf Course, and dropped off at many Cupertino senior communities. Anyone interested can also subscribe to the emailing list to receive a bi-monthly e-link to the newsletter, which is also available on the Senior Center website. Staff could expand the delivery of printed copies to appropriate facilities and households. |  |  |  |  | 3 |  | 3
45 | Councilmember Proposed Item | Single Use Plastics and Mayors Cup Challenge Current City Work Program Item Councilmember Proposal | Phase 2 of existing work program item | Unknown at this time | TBD | TBD | Unknown at this time | 100000 | 27890 | Sustainability Commission | Public Works | Sustainability and Fiscal Strategy | 10. Preserve the Environment |  |  |  |  | 3 |  |  |  | 3
46 | Councilmember Proposed Item | Visitor Center Councilmember Proposal | Develop an online and offline visitor center/guide so that visitors to Cupertino know where to go. Ideally a (digital) map to identify locations to visit or for photo ops to post on social media. Notes: - Cupertino is well-known. But besdies Apple Store, there is no points of interest. This Visitor Guide will help boost commercial sales and Cupertino's image - The Economic Develop Committee could take on the planning for this task. | Medium | 2022-07-01 | 2023-06-30 | 100,000 ($40,000 for an online visitor center, $60,000 for a physical visitor center, may require addiotnal funding depending on location. Additonal staffing may be required to operate the physical center. ) | 0 | 0 | Economic Development Committee | City Manager's Office | Public Engagement and Transparency | 6. Support Vibrant and Mixed-Use Businesses | Not Include | Given other similar items related to the visitor center or a physical store, this item can be considered for the following fiscal year once the Cupertino Store has been implemented and we have insights into how best to accomodate and promote a physical and/or virtual visitor center. |  |  |  | 3 |  |  | 3
47 | Councilmember Proposed Item | Youth Who Work Councilmember Proposal | Encourage more youth and young adults in schools to work and also help small businesses to reduce the burden caused higher minimum wages. For example, the City could provide $2/hour to compensate local small businesses. | Large | 2022-07-01 | 2023-09-30 | 70,000 (Resources required include salary for youth and access to a third-party employer of record and case management.) | 0 | 0 | Economic Development Committee | City Manager's Office | Quality of Life | 6. Support Vibrant and Mixed-Use Businesses | Include | This could be accomplished by creating a summer internship program for youth to work with small businesses. This will require extensive cooridnation with external partners. |  |  |  | 3 |  |  | 3
48 | 46 | CalTrans Adopt-a-Highway Program Staff Proposal | Coordinate with staff, volunteers and CalTrans to look for options to take over current Adopt-a-Highway obligations along highway that run through Cupertino's jurisdiction to create cleaner and more beautiful roadsides by removing litter, overgrown vegetation and other pollutants from entering state waterways through storm drains. | Medium | 2022-07-01 | 2023-06-30 | 10000 | 0 | 0 |  | Public Works | Transportation | 10. Preserve the Environment | Include | The program is part of CalTrans Clean California pilot program to restore pride in public spaces and make a difference in communities through cleaning and beautifying roadsides. There is no cost to particiate in the Adopt-a-Highway program. |  | 1 | 0 | 0 | 1 | 0.5 | 2
49 | 44 | 4) Cybersecurity Public Education Technology Information and Communications Commission Proposal | Provide education on cybersecurity to City residents, guests and businesses. | Small | 2022-07-11 | 2022-12-02 | 7500 | 0 | 0 | TICC | Innovcation Technology | Public Engagement and Transparency |  | Include | This is a repeat of a project completed 3 years ago. Commissioners will take on the majority of the work for this item, including speaker selection and facilitate presentation to Cupertino residents. |  | 0 | 0 | 1 | 1 | 0.5 | 2
50 | 36 | Privately-Owned EV Chargers Sustainability Commission Proposal | Explore options for private businesses to open up privately-owned electric vehicle chargers to the public when not in use by employees. | Medium | 2022-07-01 | 2023-06-30 | 25000 | 0 | 0 | Sustainability Commission | City Manager's Office | Sustainability and Fiscal Strategic | 10. Preserve the Environment | Not include - Operational | The City will be exploring options for EV charging access under the Building Division's update to the local green building ordinance (Reach Codes) which occurs every three years. The City is also pursuing additional publicly-owned infrastructure. |  | 0 | 0 | 1 | 1 | 0.5 | 2
51 | 32 | 4) Volunteer Engagement Strategy Public Safety Commission Proposal | Revised Objective: Develop comprehensive campaign to increase community participation in the City's volunteer programs such as Block Leaders/Neighborhood Watch and Citizen Corps. Explore existing online platforms or applications to share these volunteer opportunites. _______________________________________________________________ The objective was revised as it is not recommended to develop a stand-alone app to increase participation in volunteer programs. Public Safety Commission: Increase volunteer participation. Invest in an app or existing app to see volunteer opportunities in the city. Campaign to increase participation in Neighborhood Watch, Block Leaders, and Citizen Corps. | Large | 2022-07-01 | 2023-06-01 | 10000 | 0 | 0 | Public Safety Commission | City Manager's Office | Quality of Life | 2. Improve Public Health and Safety | Not include - Operational | This is a continued item from the Revamp the Block Leader Program. It is not recommended to pursue a new, stand-alone app for volunteer engagement. |  | 0 | 1 | 0 | 1 | 0.5 | 2
52 | 6 | Festival that is run by Fine Arts Commission Fine Arts Commission Proposal | Event run by Fine Arts Commission for the Cupertino community, in collaboration with Parks and Recreation. | Medium | 2022-07-01 | 2023-06-01 | 40000 | 0 | 0 | Fine Arts Commission | Parks and Recreation | Quality of Life |  | Not Include | The Fine Arts Commission previously worked with the current festivals to have space for fine arts by community members, award winners, etc. The number of festivals has grown since the past collaboration, which will allow for more opportunities to showcase art. If festivals were put on by the Fine Arts Commission, additional staffing will be required, as there is not enough bandwidth to take this on. |  | 0 | 1 | 0 | 0 | 0.25 | 1
53 | 18 | 2) Long-Term Strategic Plan Parks and Recreation Commission Proposal | Create a prioritization list of the 22 opportunities listed in the Parks and Recreation System Master Plan. | Large | 2022-07-01 | 2023-06-30 | 0 | 0 | 0 | Parks and Recreation Commission | Parks and Recreation | Quality of Life | 1. Develop Cohesive Neighborhoods 5. Ensure a Balanced Community | Include | Community input and Parks and Recreation Commission prioritization is necessary to organize the long-term strategic plan items pointed out in the Parks and Recreation Master Plan. |  | 1 | 0 | 0 | 0 | 0.25 | 1
54 | Councilmember Proposed Item | Regional Transformative Transit Projects Initiative Current City Work Program Item Councilmember Proposal | Work to advance the following projects as submitted to the Metropolitan Transportation Commission (MTC) as Transformative Transportation Projects: 1. Stevens Creek Corridor High Capacity Transit 2. Highway 85 Transit Guideway 3. Silicon Valley High Capacity Transit Loop 4. Transit Update & Funding Strategies | Large | 2018-04-12 | 2030-04-10 | 0 | 0 | 0 |  | Public Works | Transportation | 4. Enhance Mobility | Not include - Operational | This item is being worked on as part of operations and should be removed from the City Work Program because the projects described are ongoing and very long-term (20-30 years), have no defined schedules or milestones with frequent gaps in progress spanning years, and Cupertino has little control over ultimate project progress or success. Staff, as part of operations, will continue to have a seat at the regional table to ensure Cupertino’s interests are considered. |  |  | 1 |  |  |  | 1
55 | 27 | Solar Generation Maximization Planning Commission Proposal | Can homes be designed to maximize solar exposure for solar energy generation? Should vents be redirected to ensure that solar generation can be maximized? | N/A This is a great idea, and it is already required by the state and in place in Title 24. | N/A | N/A | N/A | 0 | 0 | Planning Commission/ Sustainability Commission | City Manager's Office | Sustainability and Fiscal Strategic | 10. Preserve the Environment | Not Include | There are existing building code requirements applicable for solar applications. Allowance for maximum solar panel installation is part of the building permit review process. https://www.energy.ca.gov/programs-and-topics/programs/building-energy-efficiency-standards/online-resource-center/solar. |  | 0 | 0 | 0 | 1 | 0.25 | 1
56 | 5 | Young Artist Scholarships Proposed by Fine Arts Commission | Provide scholarships throughout the year for young artists. Work with organizations to sponsor. | Medium | 2022-07-01 | 2023-06-01 | 1000 | 0 | 0 | Fine Arts Commission | Parks and Recreation | Quality of Life |  | Not Include - Operational | This item is already operational as the current Fine Arts Commission Artist Awards program already offers monetary awards to the winning artists. The monetary awards for this program are currently offered to the winning Youth, Emerging, and Distinguished artists. |  | 0 | 0 | 0 | 1 | 0.25 | 1